## Standards Review
ID | MAJOR ACTIVITY AND RELEVANT ISQuaEEA REQUIREMENT | SUB ACTIVITIES | RESPONSIBLE PARTY | RESOURCES REQUIRED | START DATE | COMPLETION DATE
1 | Standards revision policy and work plan updated (1.3) | Update/Develop standards revision policy Update/Develop companion plan that includes: - Activities - Resources - Timeframes | SafeCare staff (John Dekker, Annedien Plantenga) | None | 2024-01-01 | 2024-01-01
2 | Revision policy and work plan approved | Appoint new Standards Working Group Meeting minutes | SafeCare Standards Development Group | None | 2024-02-01 | 2024-02-01
3 | Standards revision plan made publicly available (1.4) | Upload revision plan to SafeCare website | SafeCare technical staff | None | 2024-02-01 | 2024-02-01
4 | Establish need/rationale for revisions (1.1) | a) Environmental scan of trends and conduct focus groups with SafeCare clients, assessors, and surveyors to detail key themes for revisions | SafeCare staff | On-line searches Zoom meetings with clients Zoom meeting with surveyors and assessors | 2024-02-01 | 2024-06-01
5 | Establish need/rationale for revisions (1.1) | b) Survey of all assessors, surveyors, client organizations, professionals, patient/service users, governments, other stakeholders | SafeCare staff | Survey monkey feedback | 2024-02-01 | 2024-04-01
6 | Establish need/rationale for revisions (1.1) | c) Analysis of data from previous surveys | SafeCare staff | Any cost related to database search | 2024-02-01 | 2024-03-01
7 | Establish need/rationale for revisions (1.1) | d) Identify experts and seek their advice | Standards Development Group and SafeCare staff | None Individual conference calls or email | 2024-02-01 | 2024-11-01
8 | Establish need/rationale for revisions (1.1) | e) Integrate all findings and display for review by Standards Development Group with minutes showing results of review | Staff and Standards Development group | Standards Development Group meeting costs | 2024-06-01 | 2024-09-01
9 | Identify any relationships of SafeCare standards to standards of other organizations (1.2) |  | SafeCare staff review | None | 2024-02-01 | 2024-07-01
10 | Basis for standards revisions is established (1.5) | Gather: - relevant research - international guidelines - WHO and other guidelines - expert input Followed by: - Integrate evidence - Map evidence to current or new standards | SafeCare staff | Standards Development Group meeting costs | 2024-09-01 | 2024-11-01
11 | Drafting of new and revised standards | Standards Development Group review | SafeCare staff | Meeting costs | 2024-07-01 | 2024-12-01
12 | Stakeholder input into revision process (1.6) | a) Circulate draft standards to stakeholder groups for their input into revision process b) Integrate findings c) Minutes from any meetings d) Standards Development Group review | SafeCare staff | Meeting costs | 2024-03-01 | 2025-01-01
13 | Scope of standards is clear (1.7) | Ensure that the introduction to the standards introduction includes: - type of organization - all or portion of organization - services covered | SafeCare staff | None | 2024-03-01 | 2025-01-01
14 | Purpose of standards is clear (1.8) | Ensure that the introduction to the standards is clear as to the purpose | SafeCare staff | None | 2025-01-01 | 2025-01-01
15 | Clarity of standards framework (1.9) | Survey clients and surveyors/assessors as to clarity of standards framework | SafeCare staff | Online Survey | 2024-03-01 | 2025-01-01
16 | Clarity of standards language (1.10) | Survey clients and surveyors/assessors as to clarity of standards language | SafeCare staff | Online Survey Meeting costs for Standards Development Group review of findings | 2024-03-01 | 2025-01-01
17 | Draft standards evaluated by clients and surveyors / assessors for RUMBA (1.11) | Survey clients and surveyors/assessors as to RUMBA (relevant, understandable, measurable, beneficial, achievable) - written plan for this - clear instructions to respondents - integrate findings - review by Standards Committee - examples of how standards changed from review | SafeCare staff | Online Survey Meeting costs for Standards Development Group review of findings | 2024-11-01 | 2025-01-01
18 | Complete drafting of standards for preliminary approval | Standards Development Group preliminary approval of standards | SafeCare staff | Meeting costs | 2024-11-01 | 2024-12-01
19 | Approval of standards (1.12) | a) Ensure approval process is in policy and that standards are approved prior to use b) Standards Development Group approval | SafeCare staff | Meeting costs | 2024-12-10 | 2024-12-10
20 | Establish when and how standards can be used by others (1.13) | a) develop policy b) specify conditions in a contract c) establish contract evaluation process | SafeCare staff | None | 2024-01-01 | 2025-01-01
21 | Implementation plan (can be part of standards development plan) (1.14) | Written plan to include: a) activities b) responsibilities c) timeframes d) any transition arrangements | SafeCare staff | None | 2025-01-01 | 2025-02-02
22 | Final approval by SafeCare Director | a) Memo to be written by SafeCare Director to announce formal approval of SafeCare Standards and date of release b) Announce release of new Standards on SafeCare website | SafeCare Director | None | 2025-02-07 | 2025-02-07
23 | Educate or inform clients and surveyors on the new or revised standards (1.15) and (2.3) | a) Written education plan b) Announcement of education on web site or other means | SafeCare staff | Meeting costs for education conferences | 2025-03-15 | 2025-03-25
24 | Feedback on new or revised standards (1.16) and (2.4) | Develop a feedback survey on new or revised standards to be used with each survey a) tools used b) feedback results c) how data is analyzed d) examples of use | SafeCare staff | Standards Development Group review of results | 2024-12-01 | 2025-01-01

## ISQua planning
MAJOR ACTIVITY | SUB ACTIVITIES | RESPONSIBLE PARTY | RESOURCES REQUIRED | START DATE | COMPLETION DATE
Complete Self-Assessment | Ensure previous Recommendations are addressed | SafeCare staff and advisors | Any costs for outside advice | 2024-11-01 | 2025-01-01
Submit Self-Assessment to ISQuaEEA for Technical Review |  | SafeCare staff | None | 2025-02-01 | 2025-02-01
Incorporate Technical Review Changes |  | SafeCare staff and advisors | Any costs for outside advisors | 2025-02-01 | 2025-02-01
Submit Final Self-Assessment to ISQuaEEA |  | SafeCare staff | None | 2025-02-01 | 2025-02-01
ISQuaEEA Survey of Standards |  | ISQuaEEA Surveyors | None | 2025-03-01 | 2025-03-01
Factual Accuracy Review by SafeCare |  | SafeCare staff | None | 2025-04-01 | 2025-04-01
ISQuaEEA Validation Review and SafeCare Response |  | ISQuaEEA Reviewer and SafeCare staff | None | 2025-04-01 | 2025-04-01
ISQua Board Review |  | ISQua Board | None | 2025-05-01 | 2025-05-01
Award Letter to SafeCare |  | ISQua Staff | None | 2025-06-01